## Dashboard
Project Management Dashboard
17-Feb-20 to 13-Mar-20
Project | Task | Manager | Start Date | End Date | Duration | Days comp. | Progress | Budget | Actual | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-22 | 2020-02-23 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | 2020-02-29 | 2020-03-01 | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-07 | 2020-03-08 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13
Alpha | Task 1 | Raj | 2020-02-28 | 2020-03-10 | 8 | 3 | 37.5% | 96000 | 32256
| Task 2 | Wood | 2020-03-02 | 2020-03-12 | 9 | 4 | 44.44% | 513000 | 226233
| Task 3 | Mike | 2020-02-20 | 2020-02-26 | 5 | 3 | 60% | 616000 | 401579
| Task 4 | Harry | 2020-02-19 | 2020-02-21 | 3 | 3 | 100% | 817000 | 807069
| Task 5 | Sam | 2020-02-21 | 2020-03-02 | 7 | 3 | 42.86% | 372000 | 173166
| Task 6 | Raj | 2020-02-24 | 2020-03-06 | 10 | 2 | 20% | 50000 | 8400
| Task 7 | Wood | 2020-02-24 | 2020-03-06 | 10 | 3 | 30% | 807000 | 262679
| Task 8 | Mike | 2020-02-24 | 2020-02-26 | 3 | 0 | 0% | 691000 | 0
Delta | Task 1 | Harry | 2020-03-02 | 2020-03-12 | 9 | 8 | 88.89% | 787000 | 727188
| Task 2 | Sam | 2020-03-02 | 2020-03-13 | 10 | 2 | 20% | 228000 | 47880
| Task 3 | Raj | 2020-02-17 | 2020-02-20 | 4 | 0 | 0% | 147000 | 0
| Task 4 | Wood | 2020-02-19 | 2020-02-28 | 8 | 5 | 62.5% | 338000 | 205123
| Task 5 | Mike | 2020-02-24 | 2020-03-06 | 10 | 3 | 30% | 857000 | 305949
| Task 6 | Harry | 2020-02-25 | 2020-03-03 | 6 | 3 | 50% | 602000 | 322371
| Task 7 | Sam | 2020-02-25 | 2020-02-28 | 4 | 2 | 50% | 990000 | 451440
Vega | Task 1 | Harry | 2020-02-17 | 2020-02-28 | 10 | 5 | 50% | 839000 | 406974
| Task 2 | Sam | 2020-02-21 | 2020-02-27 | 5 | 4 | 80% | 729000 | 487139
| Task 3 | Raj | 2020-02-24 | 2020-03-03 | 7 | 3 | 42.86% | 826000 | 298186
| Task 4 | Wood | 2020-02-26 | 2020-03-05 | 7 | 2 | 28.57% | 895000 | 280583
| Task 5 | Mike | 2020-02-28 | 2020-03-03 | 3 | 2 | 66.67% | 341000 | 129785
BETA | Task 1 | Harry | 2020-02-17 | 2020-02-21 | 5 | 2 | 40% | 218000 | 97337
| Task 2 | Sam | 2020-02-17 | 2020-02-24 | 6 | 3 | 50% | 393000 | 177440
| Task 3 | Raj | 2020-02-18 | 2020-03-02 | 10 | 4 | 40% | 86000 | 31046
| Task 4 | Wood | 2020-02-21 | 2020-03-04 | 9 | 3 | 33.33% | 732000 | 261324
| Task 5 | Mike | 2020-02-17 | 2020-02-20 | 4 | 1 | 25% | 492000 | 116850
| Task 6 | Harry | 2020-02-20 | 2020-02-27 | 6 | 0 | 0% | 188000 | 0
| Task 7 | Sam | 2020-02-20 | 2020-02-28 | 7 | 3 | 42.86% | 180000 | 79380
| Task 8 | Raj | 2020-02-24 | 2020-02-28 | 5 | 2 | 40% | 582000 | 195231
| Task 9 | Wood | 2020-02-24 | 2020-03-05 | 9 | 1 | 11.11% | 562000 | 74746
| Task 10 | Mike | 2020-02-24 | 2020-03-02 | 6 | 3 | 50% | 416000 | 175015
MTBS | Task 1 | Harry | 2020-02-18 | 2020-02-26 | 7 | 7 | 100% | 293000 | 273001
| Task 2 | Sam | 2020-02-17 | 2020-02-27 | 9 | 4 | 44.44% | 224000 | 57910
| Task 3 | Raj | 2020-02-18 | 2020-02-27 | 8 | 0 | 0% | 978000 | 0
| Task 4 | Wood | 2020-02-20 | 2020-02-28 | 7 | 3 | 42.86% | 932000 | 379157
| Task 5 | Mike | 2020-02-21 | 2020-02-26 | 4 | 1 | 25% | 854000 | 322812
| Task 6 | Harry | 2020-02-21 | 2020-02-28 | 6 | 3 | 50% | 81000 | 38461
| Task 7 | Sam | 2020-02-24 | 2020-03-02 | 6 | 5 | 83.33% | 169000 | 136468
| Task 8 | Raj | 2020-02-25 | 2020-02-28 | 4 | 1 | 25% | 61000 | 12078
| Task 9 | Wood | 2020-02-27 | 2020-03-06 | 7 | 3 | 42.86% | 645000 | 273048
| Task 10 | Mike | 2020-02-17 | 2020-02-19 | 3 | 3 | 100% | 68000 | 64987
Grand Total | [7 empty] | 19695000 | 8340291
DATE
FILTER BY
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
42%
FILTER BY
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
BUDGET
ACTUAL

## Workings (hidden)
Budget v Actual Doughnut & Bar Chart |  |  | Tasks Bar Chart |  |  | Overall Progress - Days Completed v Duration Doughnut Chart |  |  |  |  | Scroll bar position
| Actual | Budget | Not Started | 4 | =COUNTIF(Dashboard!H9:H54,"="&0) | Values |  | Doughnut Chart | % | Formula | 0
Bar Chart | 8340291 | 19695000 | In Progress | 33 | =COUNTIFS(Dashboard!H9:H54,"<>"&0,Dashboard!H9:H54,"<"&1) | Days completed | 112 | Days Completed | 42.11% | =J3/$J$4
Dougnut Chart | 42.35% | 57.65% | Completed | 3 | =COUNTIF(Dashboard!H9:H54,"="&1) | Duration | 266 | Days Remaining | 57.89% | =1-M3
|  | =1-B4 | Remaining | 37 | =F3+F2
|  |  | Total Tasks | 40 | =COUNTA(Dashboard!B9:B53)

## Data
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
BETA | Task 1 | Harry | 2020-02-17 | 5 | 2020-02-21 | 2 | 40% | 218000 | 97337
BETA | Task 2 | Sam | 2020-02-17 | 6 | 2020-02-24 | 3 | 50% | 393000 | 177440
BETA | Task 3 | Raj | 2020-02-18 | 10 | 2020-03-02 | 4 | 40% | 86000 | 31046
BETA | Task 4 | Wood | 2020-02-21 | 9 | 2020-03-04 | 3 | 33.33% | 732000 | 261324
BETA | Task 5 | Mike | 2020-02-17 | 4 | 2020-02-20 | 1 | 25% | 492000 | 116850
BETA | Task 6 | Harry | 2020-02-20 | 6 | 2020-02-27 | 0 | 0% | 188000 | 0
BETA | Task 7 | Sam | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 180000 | 79380
BETA | Task 8 | Raj | 2020-02-24 | 5 | 2020-02-28 | 2 | 40% | 582000 | 195231
BETA | Task 9 | Wood | 2020-02-24 | 9 | 2020-03-05 | 1 | 11.11% | 562000 | 74746
BETA | Task 10 | Mike | 2020-02-24 | 6 | 2020-03-02 | 3 | 50% | 416000 | 175015
MTBS | Task 1 | Harry | 2020-02-18 | 7 | 2020-02-26 | 7 | 100% | 293000 | 273001
MTBS | Task 2 | Sam | 2020-02-17 | 9 | 2020-02-27 | 4 | 44.44% | 224000 | 57910
MTBS | Task 3 | Raj | 2020-02-18 | 8 | 2020-02-27 | 0 | 0% | 978000 | 0
MTBS | Task 4 | Wood | 2020-02-20 | 7 | 2020-02-28 | 3 | 42.86% | 932000 | 379157
MTBS | Task 5 | Mike | 2020-02-21 | 4 | 2020-02-26 | 1 | 25% | 854000 | 322812
MTBS | Task 6 | Harry | 2020-02-21 | 6 | 2020-02-28 | 3 | 50% | 81000 | 38461
MTBS | Task 7 | Sam | 2020-02-24 | 6 | 2020-03-02 | 5 | 83.33% | 169000 | 136468
MTBS | Task 8 | Raj | 2020-02-25 | 4 | 2020-02-28 | 1 | 25% | 61000 | 12078
MTBS | Task 9 | Wood | 2020-02-27 | 7 | 2020-03-06 | 3 | 42.86% | 645000 | 273048
MTBS | Task 10 | Mike | 2020-02-17 | 3 | 2020-02-19 | 3 | 100% | 68000 | 64987
Vega | Task 1 | Harry | 2020-02-17 | 10 | 2020-02-28 | 5 | 50% | 839000 | 406974
Vega | Task 2 | Sam | 2020-02-21 | 5 | 2020-02-27 | 4 | 80% | 729000 | 487139
Vega | Task 3 | Raj | 2020-02-24 | 7 | 2020-03-03 | 3 | 42.86% | 826000 | 298186
Vega | Task 4 | Wood | 2020-02-26 | 7 | 2020-03-05 | 2 | 28.57% | 895000 | 280583
Vega | Task 5 | Mike | 2020-02-28 | 3 | 2020-03-03 | 2 | 66.67% | 341000 | 129785
Delta | Task 1 | Harry | 2020-03-02 | 9 | 2020-03-12 | 8 | 88.89% | 787000 | 727188
Delta | Task 2 | Sam | 2020-03-02 | 10 | 2020-03-13 | 2 | 20% | 228000 | 47880
Delta | Task 3 | Raj | 2020-02-17 | 4 | 2020-02-20 | 0 | 0% | 147000 | 0
Delta | Task 4 | Wood | 2020-02-19 | 8 | 2020-02-28 | 5 | 62.5% | 338000 | 205123
Delta | Task 5 | Mike | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 857000 | 305949
Delta | Task 6 | Harry | 2020-02-25 | 6 | 2020-03-03 | 3 | 50% | 602000 | 322371
Delta | Task 7 | Sam | 2020-02-25 | 4 | 2020-02-28 | 2 | 50% | 990000 | 451440
Alpha | Task 1 | Raj | 2020-02-28 | 8 | 2020-03-10 | 3 | 37.5% | 96000 | 32256
Alpha | Task 2 | Wood | 2020-03-02 | 9 | 2020-03-12 | 4 | 44.44% | 513000 | 226233
Alpha | Task 3 | Mike | 2020-02-20 | 5 | 2020-02-26 | 3 | 60% | 616000 | 401579
Alpha | Task 4 | Harry | 2020-02-19 | 3 | 2020-02-21 | 3 | 100% | 817000 | 807069
Alpha | Task 5 | Sam | 2020-02-21 | 7 | 2020-03-02 | 3 | 42.86% | 372000 | 173166
Alpha | Task 6 | Raj | 2020-02-24 | 10 | 2020-03-06 | 2 | 20% | 50000 | 8400
Alpha | Task 7 | Wood | 2020-02-24 | 10 | 2020-03-06 | 3 | 30% | 807000 | 262679
Alpha | Task 8 | Mike | 2020-02-24 | 3 | 2020-02-26 | 0 | 0% | 691000 | 0
Formulas:
End Date = WORKDAY.INTL(Table1[[#This Row],[Start Date]]-1,Table1[[#This Row],[Duration]],1)